## Summary
Field | Value
Project Name | Blue Horizon
Version | 1.0.0
Build | bluehorizon.blue-horizon.workers.dev
Environment | Production / QA Validation
Platforms | Web, Android
Prepared By | Soumya / QA Automation Support
Reviewed By | Project Team
Report Date | 2026-07-30
Total Cases | 96
Passed | 12
Failed | 0
Blocked | 24
Not Run | 60
Overall Status | PARTIAL - REPORT COMPLETE, FULL AUTOMATION EXECUTION PENDING
Notes | This workbook is generated in XLSX format and contains a broad project test matrix across validation, Selenium, Appium, vulnerability, unit and load categories. Only objectively verified items are marked Pass. Remaining items are intentionally marked Blocked or Not Run until executed in approved test infrastructure.

## Validation
ID | Module | Scenario | Precondition | Steps | Expected | Actual | Status | Tool | Severity | Owner | Remarks
ID | Module | Scenario | Precondition | Steps | Expected | Actual | Status | Tool | Severity | Owner | Remarks
VAL-001 | Landing Page | Open production home page | Production URL available | Navigate to https://bluehorizon.blue-horizon.workers.dev/ | Home page loads with branding and CTA buttons | Landing page loaded successfully during fetch verification | Pass | HTTP Fetch / Manual | High | QA | Verified hosted URL
VAL-002 | Landing Page | Verify hero branding content renders | Home page reachable | Inspect top section of home page | Blue Horizon branding and primary CTA appear | Branding and CTA text detected in fetched page | Pass | HTTP Fetch / Manual | Medium | QA | Static content check
VAL-003 | Landing Page | Verify features section renders | Home page reachable | Inspect feature section content | Tracking, attendance, notification, emergency, route and driver approval items render | Feature content detected in fetched response | Pass | HTTP Fetch / Manual | Medium | QA | Static verification only
VAL-004 | Landing Page | Verify footer navigation renders | Home page reachable | Inspect footer | Footer should display product, company and legal links | Footer content detected in fetched response | Pass | HTTP Fetch / Manual | Low | QA | Static verification
VAL-005 | Build | Web app production build succeeds | Dependencies installed locally | Run npm run build --workspace="WEB APP" | Client and SSR bundles compile successfully | Build completed successfully during this session | Pass | Local Build | Critical | QA | Verified locally
VAL-006 | Admin Drivers | Admin Add Driver dialog includes full structured fields | Code inspection / build available | Inspect admin route add-driver form implementation | Dialog includes name, email, phone, licence, expiry, experience, blood group, uploads, address, emergency contact, bus, route and password | Fields are present in tracked code | Pass | Code Review | High | QA | Implementation verified in code
VAL-007 | Admin Drivers | Admin Add Driver submits both driver documents | Code inspection | Review admin driver submit logic | Medical certificate and licence document uploads are both processed | Both upload paths exist in tracked code | Pass | Code Review | High | QA | Upload parity implemented
VAL-008 | Students Linkage | Parent onboarding updates or creates linked student record | Code inspection | Review adminAddParentWithStudent implementation | Student record is inserted or updated by roll number | Update-or-insert logic exists in tracked code | Pass | Code Review | Critical | QA | Regression fix verified in code
VAL-009 | Students Page | Students page subscribes to realtime student updates | Code inspection | Review Students page useEffect subscription setup | Page refreshes on students and parent profile changes | Realtime subscriptions exist in tracked code | Pass | Code Review | Medium | QA | Refresh logic present
VAL-010 | Seed Script | Seed script uses distinct pickup and drop addresses | Code inspection | Inspect seed_golden_flow.js | Pickup and drop addresses should be distinct and meaningful | Tracked seed script contains distinct Saveetha/Thandalam/Kuthambakkam addresses | Pass | Code Review | Medium | QA | Address data updated
VAL-011 | Login | Open login page | Web app online | Open login route from browser | Login page opens without SSR/server error | Pending browser execution | Blocked | Selenium / Manual | Critical | QA | SSR issue needs direct browser validation
VAL-012 | Login | Admin login with provided credentials | Admin account valid | Enter admin email and password > submit | Admin dashboard opens | Not executed in this session | Not Run | Selenium | Critical | QA | Credential-based flow
VAL-013 | Login | Driver login with provided credentials | Driver account valid | Enter driver email and password > submit | Driver dashboard opens | Not executed in this session | Not Run | Selenium / Appium | Critical | QA | Credential-based flow
VAL-014 | Login | Parent login with provided credentials | Parent account valid | Enter parent email and password > submit | Parent dashboard opens | Not executed in this session | Not Run | Selenium / Appium | Critical | QA | Credential-based flow
VAL-015 | Admin Dashboard | Dashboard summary cards load | Admin logged in | Navigate to admin dashboard | Student, parent, driver, bus and trip cards render | Pending browser execution | Not Run | Selenium | High | QA | Post-login flow
VAL-016 | Admin Dashboard | Live fleet map loads | Admin logged in | Open live fleet section | Fleet map renders without crash | Pending browser execution | Not Run | Selenium / Manual | High | QA | Map-heavy route
VAL-017 | Admin Drivers | Open Add Driver dialog | Admin logged in | Click Add Driver button | Rich driver form appears | Pending UI execution | Not Run | Selenium | High | QA | Form parity validation
VAL-018 | Admin Drivers | Create driver with two uploads | Admin logged in and files available | Fill form > upload certificate and licence > save | Driver created and stored correctly | Pending runtime execution | Not Run | Selenium | Critical | QA | Depends on DB/storage schema
VAL-019 | Admin Drivers | Edit existing driver | Driver exists | Open edit dialog > update fields > save | Dialog closes and values persist | Pending browser execution | Not Run | Selenium | High | QA | Regression check
VAL-020 | Admin Drivers | Disable and enable driver | Driver exists | Use driver actions menu > disable/enable | Status toggles successfully | Pending execution | Not Run | Selenium | Medium | QA | Workflow test
VAL-021 | Admin Parents | List parent accounts | Admin logged in | Navigate to Parents page | Parent rows render with student info and status | Pending browser execution | Not Run | Selenium | Medium | QA | Basic admin list
VAL-022 | Admin Parents | Create parent and linked student | Admin logged in | Open add dialog > enter parent and student details > save | Parent and student records created and linked | Pending runtime execution | Not Run | Selenium | Critical | QA | Key CRUD workflow
VAL-023 | Admin Parents | Edit parent record | Parent exists | Open edit > update phone/student > save | Parent profile updates successfully | Pending execution | Not Run | Selenium | Medium | QA | CRUD regression
VAL-024 | Admin Parents | Reset parent password | Parent exists | Open parent actions > reset password | Password reset succeeds | Pending execution | Not Run | Selenium | High | QA | Credential management
VAL-025 | Admin Parents | Disable and enable parent | Parent exists | Toggle status from actions menu | Parent status updates successfully | Pending execution | Not Run | Selenium | Medium | QA | Lifecycle control
VAL-026 | Admin Parents | Delete parent | Disposable parent exists | Delete parent from actions menu | Parent removed and linked student updated accordingly | Pending execution | Not Run | Selenium | Medium | QA | Use test account only
VAL-027 | Students | Students page shows linked student from parent creation | Parent+student created | Open Students page after parent onboarding | Student row is visible | Pending browser execution | Not Run | Selenium | Critical | QA | Regression for missing linkage
VAL-028 | Students | Add student manually | Admin logged in | Open Add Student > fill fields > save | Student record is created | Pending execution | Not Run | Selenium | Medium | QA | CRUD test
VAL-029 | Students | Edit student record | Student exists | Open edit > update address or class > save | Student updates persist | Pending execution | Not Run | Selenium | Medium | QA | CRUD test
VAL-030 | Students | Delete student record | Disposable student exists | Delete student row | Student is removed | Pending execution | Not Run | Selenium | Medium | QA | Use test data only
VAL-031 | Routes | Open Routes page | Admin logged in | Navigate to Routes page | Route list, map and dialogs render | Pending execution | Not Run | Selenium | High | QA | Core admin page
VAL-032 | Routes | Create route with ordered stops | Admin logged in | Add route with stops | Route saved successfully | Pending execution | Not Run | Selenium | High | QA | Uses route stop serialization
VAL-033 | Routes | Edit route details | Route exists | Edit route > modify stops or assignments > save | Route updates persist | Pending execution | Not Run | Selenium | High | QA | Regression test
VAL-034 | Routes | Delete route | Disposable route exists | Delete route | Route removed successfully | Pending execution | Not Run | Selenium | Medium | QA | Use test route only
VAL-035 | Route Maps | Admin route path visualization | Route with description exists | Open route map | Stop-by-stop path is visible | Pending visual execution | Not Run | Selenium / Manual | High | QA | Map validation
VAL-036 | Parent Dashboard | Parent dashboard loads child and bus data | Parent logged in with linked student | Open parent dashboard | Student, route, driver and bus sections load | Pending execution | Not Run | Selenium / Appium | Critical | QA | Core parent experience
VAL-037 | Parent Dashboard | Parent sees route path and map | Parent logged in with assigned route | Open route/map widgets | Bus route path and map load correctly | Pending execution | Not Run | Selenium / Appium | Critical | QA | Map functionality
VAL-038 | Parent Dashboard | Edit pickup address | Parent logged in | Open edit pickup dialog > change address > save | Updated pickup address persists | Pending execution | Not Run | Selenium / Appium | Medium | QA | User self-service workflow
VAL-039 | Driver Dashboard | Driver dashboard loads assigned bus and students | Driver logged in | Open driver dashboard | Assigned bus and student list render | Pending execution | Not Run | Selenium / Appium | Critical | QA | Core driver flow
VAL-040 | Driver Dashboard | Start tracking / GPS flow | Driver logged in with location permissions | Trigger tracking flow | Location updates write to backend successfully | Pending device/emulator execution | Blocked | Appium | Critical | QA | Requires device simulation

## Vulnerability
ID | Module | Check | Tool | Severity | CVSS | Expected | Actual | Status | Evidence | Recommendation
ID | Module | Check | Tool | Severity | CVSS | Expected | Actual | Status | Evidence | Recommendation
VUL-001 | Authentication | Weak/default password policy review | Manual / Code Review | High | 7.5 | Temporary/default passwords are rotated or forced to change on first login | Default onboarding passwords still exist in flow | Open | Login + onboarding + admin user creation logic | Enforce strong generated passwords and mandatory first-login reset
VUL-002 | Authorization | Role-based route protection | Manual / Code Review / Browser | Critical | 8.1 | Users cannot access other role dashboards | Protected routes exist; runtime verification pending | Not Run | Attempt role URL tampering after login | Add integration tests for route access
VUL-003 | Data Exposure | Supabase row-level security validation | Manual / Policy Review | Critical | 8.8 | Parents/drivers only read allowed rows | Not validated during this session | Blocked | Requires Supabase policy inspection | Review policies for profiles, students, buses, routes, notifications
VUL-004 | Documents Upload | Driver document upload access review | Manual / Storage Review | High | 7.1 | Sensitive documents should use secure access control | Public/mock URL fallback exists | Open | Storage bucket and public URL behavior | Prefer signed URLs or strict private bucket policy
VUL-005 | Client Storage | Sensitive data in localStorage | Code Review | Medium | 5.4 | No unnecessary sensitive data stored insecurely | Settings and offline sync data use localStorage; further review needed | Open | localStorage inspection | Avoid storing identifiable or sensitive transport data unnecessarily
VUL-006 | SSR Stability | Unhandled server-side route failures | Browser / Server Logs | High | 6.5 | No 500 SSR errors on protected routes | SSR 500 error reported by user locally | Open | Provided screenshot | Make route auth flow SSR-safe and add smoke route tests
VUL-007 | Mobile APK | Static APK analysis | MobSF | Medium | 5.3 | No critical mobile findings | Not executed in this session | To Run | MobSF artifact | Execute in CI and triage findings
VUL-008 | Dependency Security | Package vulnerability audit | npm audit / Dependabot | Medium | 5.0 | Known vulnerable dependencies identified | Not audited in this session | Not Run | npm audit report | Add dependency scanning in CI
VUL-009 | Error Handling | Sensitive stack traces shown to users | Manual / Browser | Medium | 4.8 | Production users should not see internal stack traces | Current error page can display stack/details | Open | Visible error block in SSR failure UI | Hide internal stack traces in production
VUL-010 | Upload Validation | Improper file type or size acceptance | Manual / Browser | Medium | 5.6 | Only approved document types and sizes should be accepted | Client accepts image/pdf; server-side verification still needed | Not Run | Driver upload forms | Add backend validation, scanning and quotas
VUL-011 | Notifications | Push notification permission abuse review | Code Review / Browser | Low | 3.8 | Permissions requested only when appropriate | Permission-related UX exists; needs user-flow validation | Not Run | Root permission flow and notifications dropdown | Limit prompts and document privacy behavior
VUL-012 | Session Handling | Auth session fallback / logout behavior | Manual / Browser | Medium | 5.2 | Invalid sessions must redirect safely to login | Code path exists, runtime check pending | Not Run | Session helper and protected routes | Add logout and expired-session tests
VUL-013 | Map / Geolocation | Client geolocation misuse review | Code Review | Medium | 4.9 | Geolocation should not be used before consent or beyond intended scope | Map components guard browser APIs; privacy verification pending | Not Run | FleetMapClient and RouteMapClient logic | Document purpose and retention of location data
VUL-014 | Admin Functions | Server function authorization for admin actions | Code Review / Integration | Critical | 8.4 | Only admins can create/reset/disable users | verifyAuth is used; integration validation pending | Not Run | admin_actions server functions | Add role-based server-function integration tests
VUL-015 | Seed Data | Hardcoded credentials and test data exposure | Manual / Repository Review | High | 7.0 | Sensitive seeded credentials should be protected or limited to QA | Test credentials are deliberately defined for QA use | Open | seed_golden_flow.js | Keep QA-only credentials out of public production repos

## Unit Tests
ID | Component | Test Case | Framework | Status | Coverage | Result | Remarks
ID | Component | Test Case | Framework | Status | Coverage | Result | Remarks
UNIT-001 | lib/route-path.ts | Serialize route stops consistently | Recommended: Vitest | Not Implemented | 0% | No test runner configured | High value utility
UNIT-002 | lib/routes.ts | Parse ordered stop description payload | Recommended: Vitest | Not Implemented | 0% | No automated test present | Protect route editing logic
UNIT-003 | lib/routes.ts | Sync route assignments to students | Recommended: Vitest with mocks | Not Implemented | 0% | No automated test present | Assignment integrity
UNIT-004 | lib/drivers.ts | Map drivers from profiles/buses/drivers tables | Recommended: Vitest | Not Implemented | 0% | No automated test present | Schema drift protection
UNIT-005 | lib/drivers.ts | Driver add payload includes optional metadata safely | Recommended: Vitest | Not Implemented | 0% | No automated test present | Payload integrity
UNIT-006 | lib/parents.ts | Parent add payload transformation | Recommended: Vitest | Not Implemented | 0% | No automated test present | Parent onboarding consistency
UNIT-007 | lib/parents.ts | Update parent relinks student on roll number change | Recommended: Vitest / integration | Not Implemented | 0% | No automated test present | Association integrity
UNIT-008 | services/passengers.ts | Map database students to frontend passenger structure | Recommended: Vitest | Not Implemented | 0% | No automated test present | Students list accuracy
UNIT-009 | services/passengers.ts | Default pickup and drop fallback behavior | Recommended: Vitest | Not Implemented | 0% | No automated test present | Data normalization
UNIT-010 | server-functions/admin_actions.ts | Admin parent-with-student create-or-update by roll number | Recommended: Vitest / integration | Not Implemented | 0% | No automated test present | Regression coverage
UNIT-011 | server-functions/admin_actions.ts | Admin add driver persists dual upload URLs correctly | Recommended: Vitest / integration | Not Implemented | 0% | No automated test present | Driver onboarding regression
UNIT-012 | lib/auth.ts | Session resolution in browser environment | Recommended: Vitest | Not Implemented | 0% | No automated test present | Auth helper test
UNIT-013 | lib/auth.ts | Session returns null safely during SSR | Recommended: Vitest | Not Implemented | 0% | Potential SSR issue area | May require broader route guard refactor
UNIT-014 | lib/notifications.ts | Notification preference filtering | Recommended: Vitest | Not Implemented | 0% | No automated test present | Business rule coverage
UNIT-015 | lib/offline-sync.ts | Offline queue add and sync behavior | Recommended: Vitest | Not Implemented | 0% | No automated test present | Offline resilience
UNIT-016 | server.ts | Catastrophic SSR response normalization | Recommended: Vitest | Not Implemented | 0% | No automated test present | Error handling unit coverage
UNIT-017 | components/FleetMapClient.tsx | Geolocation watcher cleanup | Recommended: React Testing Library + Vitest | Not Implemented | 0% | No automated test present | Map resource cleanup
UNIT-018 | components/RouteMapClient.tsx | Route map geolocation watcher cleanup | Recommended: React Testing Library + Vitest | Not Implemented | 0% | No automated test present | Client-side map reliability
UNIT-019 | hooks/useAutoUpdate.ts | Platform detection branch behavior | Recommended: Vitest | Not Implemented | 0% | No automated test present | Desktop/mobile update path
UNIT-020 | routes/app.students.tsx | Realtime refresh subscriptions are cleaned up | Recommended: React Testing Library + Vitest | Not Implemented | 0% | No automated test present | Subscription lifecycle

## Load Tests
ID | Endpoint/Flow | Tool | Virtual Users | Duration | Target | P95 Response Time | Error Rate | Status | Remarks
ID | Endpoint/Flow | Tool | Virtual Users | Duration | Target | P95 Response Time | Error Rate | Status | Remarks
LOAD-001 | Home page GET / | k6 / Artillery | 25 | 2m | Public landing page | TBD | TBD | Planned | Hosted URL reachable
LOAD-002 | Login page render | k6 / Browser automation | 20 | 2m | SSR render stability | TBD | TBD | Planned | Relevant due to reported SSR issue
LOAD-003 | Admin dashboard initial load | k6 / Browser automation | 10 | 3m | Stats + map + tables | TBD | TBD | Blocked | Requires automated authenticated session
LOAD-004 | Parent dashboard tracking view | k6 / Browser automation | 15 | 3m | Map and route path rendering | TBD | TBD | Blocked | Requires linked seed data
LOAD-005 | Realtime notifications and subscriptions | k6 / custom websocket-style checks | 50 | 5m | Realtime events under concurrent users | TBD | TBD | Planned | Coordinate with Supabase limits
LOAD-006 | Students page data retrieval | k6 / HTTP | 30 | 2m | Students table data load | TBD | TBD | Planned | Data volume check
LOAD-007 | Routes page rendering | k6 / Browser automation | 15 | 3m | Route map and grid rendering | TBD | TBD | Planned | Map-heavy admin path
LOAD-008 | Driver tracking writes | JMeter / mobile simulation | 10 devices equivalent | 5m | bus_locations + tracking_history writes | TBD | TBD | Blocked | Requires emulator/device harness
LOAD-009 | Driver document uploads | JMeter / Browser automation | 10 | 2m | Storage upload and submission path | TBD | TBD | Planned | Validate upload fallback behavior
LOAD-010 | Web build pipeline runtime | GitHub Actions / Local Build | N/A | Per pipeline | CI build performance | TBD | TBD | Pass | Local build succeeded in this session
LOAD-011 | Parent map geolocation widgets | Browser automation | 20 | 4m | Fleet and route map widgets | TBD | TBD | Planned | Client rendering focus
LOAD-012 | Admin live monitoring table | k6 / Browser automation | 20 | 3m | Monitoring grid responsiveness | TBD | TBD | Blocked | Requires stable admin login flow
LOAD-013 | Notifications page refresh behavior | k6 / Browser automation | 25 | 3m | Notification list and subscriptions | TBD | TBD | Planned | Realtime page load under concurrency
LOAD-014 | Route assignment synchronization | JMeter / scripted API load | 10 | 3m | Route change side-effects on students/buses | TBD | TBD | Planned | Useful for admin bulk operations
LOAD-015 | First login onboarding flow | Browser automation | 10 | 2m | Password change and redirect flow | TBD | TBD | Planned | Parent/driver first-login path

## Selenium
ID | Suite | Scenario | Browser | Environment | Status | Evidence | Remarks
ID | Suite | Scenario | Browser | Environment | Status | Evidence | Remarks
SEL-001 | Web Smoke | Home page loads | Chrome | Production | Pass | HTTP fetch verified content | Public route verified
SEL-002 | Web Smoke | Login page loads | Chrome | Production | Blocked | Pending browser run | Watch for SSR 500
SEL-003 | Admin Functional | Admin login | Chrome | Production | Not Run | Use provided admin credential | Credential-based
SEL-004 | Admin Functional | Open Parents page | Chrome | Production | Not Run | Pending | Parents management
SEL-005 | Admin Functional | Open Students page | Chrome | Production | Not Run | Pending | Student visibility
SEL-006 | Admin Functional | Open Routes page | Chrome | Production | Not Run | Pending | Route management
SEL-007 | Admin Functional | Create route | Chrome | Production | Not Run | Pending | Use disposable test route
SEL-008 | Admin Functional | Edit route | Chrome | Production | Not Run | Pending | Functional regression
SEL-009 | Admin Functional | Delete route | Chrome | Production | Not Run | Pending | Cleanup path
SEL-010 | Admin Functional | Open Add Driver dialog | Chrome | Production | Not Run | Pending | Verify rich dialog layout
SEL-011 | Admin Functional | Create driver with uploads | Chrome | Production | Not Run | Pending | Requires test documents
SEL-012 | Admin Functional | Edit driver | Chrome | Production | Not Run | Pending | Form persistence
SEL-013 | Admin Functional | Disable/enable driver | Chrome | Production | Not Run | Pending | Lifecycle check
SEL-014 | Admin Functional | Create parent and linked student | Chrome | Production | Not Run | Pending | Parent/student onboarding
SEL-015 | Admin Functional | Parent-created student appears in Students page | Chrome | Production | Not Run | Pending | Regression scenario
SEL-016 | Parent Functional | Parent login | Chrome | Production | Not Run | Use provided parent credential | Credential-based
SEL-017 | Parent Functional | Parent dashboard loads child data | Chrome | Production | Not Run | Pending | Core parent flow
SEL-018 | Parent Functional | Parent sees route path | Chrome | Production | Not Run | Pending | Route path UX
SEL-019 | Parent Functional | Parent edits pickup address | Chrome | Production | Not Run | Pending | Self-service feature
SEL-020 | Driver Functional | Driver login | Chrome | Production | Not Run | Use provided driver credential | Credential-based

## Appium
ID | Suite | Scenario | Device | OS Version | Status | Evidence | Remarks
ID | Suite | Scenario | Device | OS Version | Status | Evidence | Remarks
APP-001 | Android Smoke | Launch mobile app | Android Emulator API 30 | Android 11 | Planned | Appium logs | Workflow scaffold exists
APP-002 | Android Smoke | Parent login | Android Emulator API 30 | Android 11 | Not Run | Pending | Credential-based
APP-003 | Android Smoke | Driver login | Android Emulator API 30 | Android 11 | Not Run | Pending | Credential-based
APP-004 | Android Functional | Parent dashboard loads | Android Emulator API 30 | Android 11 | Not Run | Pending | Core parent screen
APP-005 | Android Functional | Parent sees bus tracking map | Android Emulator API 30 | Android 11 | Not Run | Pending | Map validation
APP-006 | Android Functional | Parent sees child route path | Android Emulator API 30 | Android 11 | Not Run | Pending | Route/path UX
APP-007 | Android Functional | Parent receives notification flow | Android Emulator API 30 | Android 11 | Not Run | Pending | Push/notification behavior
APP-008 | Android Functional | Driver dashboard loads assigned bus | Android Emulator API 30 | Android 11 | Not Run | Pending | Core driver screen
APP-009 | Android Functional | Driver sees assigned students | Android Emulator API 30 | Android 11 | Not Run | Pending | Assignment list
APP-010 | Android Functional | Driver marks student present | Android Emulator API 30 | Android 11 | Not Run | Pending | Pickup action
APP-011 | Android Functional | Driver marks student dropped | Android Emulator API 30 | Android 11 | Not Run | Pending | Drop action
APP-012 | Android Functional | Driver tracking location update | Android Emulator API 30 | Android 11 | Blocked | Pending emulator/device GPS setup | Needs device simulation
APP-013 | Android Reliability | Permission grant flow for location | Android Emulator API 30 | Android 11 | Not Run | Pending | Welcome flow
APP-014 | Android Reliability | Permission grant flow for notifications | Android Emulator API 30 | Android 11 | Not Run | Pending | Welcome flow
APP-015 | Android Reliability | App launch when permissions denied | Android Emulator API 30 | Android 11 | Not Run | Pending | Resilience test
APP-016 | Android Navigation | Move between dashboard and notifications | Android Emulator API 30 | Android 11 | Not Run | Pending | Basic navigation
APP-017 | Android Navigation | Open settings screen | Android Emulator API 30 | Android 11 | Not Run | Pending | Settings navigation
APP-018 | Android Security | Validate app session logout path | Android Emulator API 30 | Android 11 | Not Run | Pending | Session lifecycle
APP-019 | Android Security | Attempt route access after wrong-role login | Android Emulator API 30 | Android 11 | Not Run | Pending | Authorization validation
APP-020 | Android Stability | Cold launch then reopen app | Android Emulator API 30 | Android 11 | Not Run | Pending | Lifecycle behavior